## Slide 1: [Client Name] [Project Name] Governance Kickoff
Onboarding for Project Managers staffed on professional services projects

## Slide 2
WHY WE'RE HERE TODAY
PART 1
15 min
How Toptal projects work
01
Who you represent
02
Roles and responsibilities
03
Delivery lifecycle
04
Decision rights and boundaries
PART 2
20 min
Your project
05
Project at a glance
06
Contract walkthrough
07
Baseline walkthrough
08
Immediate priorities
Notes: Table Slides
  Severity

## Slide 3: How Toptal Projects Work

## Slide 4
WHO YOU REPRESENT
 | Talent Engagement | Professional Services Project
You work for | The client, as an extension of their team | Toptal, leading delivery on Toptal’s behalf
The work is defined by | The client | The contract
Toptal is accountable for | Finding the right talent with sufficient capacity to meet client needs | Contracted outcomes, deliverables, schedule, and budget
Health is judged by | Client perception of your performance | An independent PMO rating against contracted outcomes
A new client request | Is assigned by the client and worked by the talent | Is logged, assessed for impact, and mutually agreed to before work begins
Core principle: The contract defines the work. Client requests do not automatically become authorized work.
Two delivery models, two different jobs
Notes: Table Slides
  Severity

## Slide 5
Three roles govern every professional services project
VALUE REALIZATION
Delivery Manager
Outcomes advocate
Advocates for client outcomes
Keeps stakeholders aligned
Owns value realization for the project
Leads the client conversation when delivery is at risk
DELIVERY ASSURANCE
PMO Portfolio Lead
The independent auditor
Independent and PMI-certified
Sets day-one baselines (WBS, RAID)
Flags unplanned scope and unassessed risks / blockers
Issues the health rating; drafts the status report
Enforces execution standards
PROJECT EXECUTION
Project Manager
The day-to-day leader
Coordinates daily work and sprints
Maintains the RAID log and schedule
Produces the delivery evidence
ROLES & RESPONSIBILITIES
Notes: Table Slides
  Severity

## Slide 6
1 · THE PLAN
Own a current, credible delivery plan
Keep the plan current and know what threatens it. The plan is not a collection of Jira tickets; you are accountable for the big picture.
2 · THE WORK
Drive execution within the approved plan
Drive the team’s work, dependencies, actions and issue resolution. Run stand-ups, follow up on actions, and check deliverable readiness.
THE DECISION LOOP
3 · Propose
Bring proposed decisions to Toptal with context, impact, options and a recommended solution.
→
4 · Get approval
Obtain Toptal approval before changing the agreed approach or making commitments to the client.
→
5 · Implement and track
Implement the agreed decision and track it through to completion.
The Project Manager owns the plan and the day-to-day work
ROLES & RESPONSIBILITIES
Notes: Table Slides
  Severity

## Slide 7
DELIVERY METHODOLOGY PHASES
PMO GOVERNANCE PHASES (OVERLAY)
Readiness
Owner: PMO
Planning
(Mobilize)
Owner: PMO → PM
Project Execution
Owner: PM · PMO verifies
Acceptance & Closure
Owner: PM → PMO
1 Readiness
Sales handoff
2 Mobilize & Align
Project Success Review
3 Discovery
Requirements, Tech Solution, & Design Review
4 Build
Test Readiness Review
5 Validate
UAT
6 Deploy
Production Readiness Review
7 Transition
Final Acceptance
DELIVERY LIFECYCLE
One governance model, across the whole lifecycle
Notes: This slide puts two things we've described separately onto one picture.
Across the top are the seven phases of how we actually deliver a project: Readiness, Mobilize and Align, Discovery, Build, Validate, Deploy, Transition.
Underneath is how PMO governs across that same lifecycle. Readiness and Mobilize map directly onto our first two governance phases.
Project Execution as a governance phase spans four delivery phases at once: Discovery, Build, Validate, and Deploy.
Governance during that window isn't a single checkpoint, it's continuous — value realization, project health, risk, forecasting, scope change, and escalation are all running in parallel with the actual delivery work.
Acceptance and Closure then map onto Transition.

## Slide 8
WEEKLY GOVERNANCE RHYTHM
1
Weekly check-in
The PMO, DM and PM review progress, scope and blockers together.
2
PMO assessment
The PMO independently issues the project’s health rating and drafts the weekly status report.
3
Reality, impact, fix
PMO gives the DM and PM what's really happening, what it means, and how we're fixing it.
4
Client Informed
The DM leads the delivery response with the client. Bad news arrives early, with a plan attached.
30 MINUTES · WEEKLY · ALL THREE ROLES
Talent PM
Plan, milestones, dependencies, decisions, actions, acceptance evidence — current as of the meeting.
Delivery Manager
Client signal: perception, expectation gaps, change on the horizon, decisions pending.
PMO
Baseline variance, burn, margin position, and the open escalation set.
DELIVERY LIFECYCLE
The weekly governance check-in
Notes: This slide puts two things we've described separately onto one picture.
Across the top are the seven phases of how we actually deliver a project: Readiness, Mobilize and Align, Discovery, Build, Validate, Deploy, Transition.
Underneath is how PMO governs across that same lifecycle. Readiness and Mobilize map directly onto our first two governance phases.
Project Execution as a governance phase spans four delivery phases at once: Discovery, Build, Validate, and Deploy.
Governance during that window isn't a single checkpoint, it's continuous — value realization, project health, risk, forecasting, scope change, and escalation are all running in parallel with the actual delivery work.
Acceptance and Closure then map onto Transition.

## Slide 9
Scenarios: requests and blockers
DECISION RIGHTS IN PRACTICE
WHAT YOU DO
“While you’re in there, can you add one more report?
Acknowledge the request without committing. Update the RAID log, check the ask against the contract scope, and assess effort and schedule impact.
Engage Toptal. Schedule time with the DM and PMO to discuss path forward.
WHAT YOU DO
Log the blocker in the RAID log. Do not swap the contracted outcome for a workaround or other activity to be productive or charge time.
Engage Toptal. Escalate to the DM and PMO if the block persists > 2 days. No workaround that changes the approach.
WHAT YOU DO
Thank the sponsor but redirect to the project scope. Update the RAID log.
Engage Toptal. Inform the DM who routes it to the Account Team if it is a new opportunity.
Day 3, still no environment access. The team offers to start in Toptal’s own environment.
A client sponsor starts assigning the team work on another initiative.
To keep commitments consistent, if a decision changes what Toptal delivers, when (dates), effort, or project team roles, engage the DM and PMO. Decisions around task sequencing, assignment, or plan refinements are yours to make.
Notes: Table Slides
  Severity

## Slide 10
Scenarios: schedule, acceptance and status
DECISION RIGHTS IN PRACTICE
WHAT YOU DO
“Can we bring the milestone forward two weeks?”
Acknowledge the request without committing. Log it, check it against the contract scope, and assess the impact on the plan, team and dependencies.
Engage Toptal. Discuss with DM and PMO. DM gives the client the answer and the trade-offs.
WHAT YOU DO
Thank the sponsor and let them know a formal acceptance sign-off will be sent.
Engage Toptal. Inform PMO to trigger deliverable or milestone acceptance.
WHAT YOU DO
Report progress against contracted deliverables, not activity. Update the schedule and RAID log with the facts.
Engage Toptal. Raise it at the weekly check-in. The PMO issues the health rating.
In a demo the sponsor says “Looks great, we’re happy.”
The client is happy and the team is busy, but contracted deliverables are behind plan.
To keep commitments consistent, if a decision changes what Toptal delivers, when (dates), effort, or project team roles, engage the DM and PMO. Decisions around task sequencing, assignment, or plan refinements are yours to make.
Notes: Table Slides
  Severity

## Slide 11: Project Details

## Slide 12: The people delivering this project
YOUR TEAM
Kris Wu
Delivery Manager
Vancouver, Canada
James Kyle West
Tech Lead
Centennial, CO
David Diatikar
Project / Product Manager
San Antonio, TX

## Slide 13: Why we’re here
PROJECT SUCCESS AGREEMENT
Our draft understanding — please confirm, correct, or add.
Why are we doing this?
Equus’s JD Edwards EnterpriseOne environment (28 workloads) runs on general-purpose Azure VMs. It sits on an unsupported legacy stack: JDE E1 8.0, SQL Server 2000, Windows Server 2003, and Windows XP dev seats. There is no formalized DR, backup governance, or SLA. This engagement relocates the environment onto a secure, supported, and governed Oracle Cloud Infrastructure (OCI) platform without changing the application.
What problem are we solving?
Unsupported operating systems and databases have limited security containment
No formalized disaster recovery, backup governance, or SLAs
Operational ownership is fragmented and support is reactive
Azure configuration is not fully documented, and some JDE 8.0 dependencies are undocumented
What does success look like?
All 28 workloads migrated to OCI with no application change and zero planned data loss
Production cutover completed in a weekend window, with go/no-go checkpoints and full rollback capability
Performance on OCI validated against current production: JDE login, order entry, financial reporting, package builds, batch execution, and records-per-minute throughput
Existing integrations (Workday, Databricks, Control-M, SSIS) working after migration
Formal, tested DR and backup with SLA-backed availability
Legacy OS/DB contained within security enclaves with compensating controls
Environment handed off to steady-state managed operations

## Slide 14: Solution Overview What we will deliver
A host-first, lift-and-shift migration of Rimage’s JD Edwards EnterpriseOne 8.0 estate from Microsoft Azure to a purpose-built OCI landing zone. The application, data, and versions stay unchanged. Legacy operating systems and databases are placed inside segmented security enclaves with virtual patching and continuous monitoring. Private connectivity to the Rimage corporate network runs over Oracle FastConnect with a redundant VPN. Work runs in six phases over about 18 weeks: Discovery & Planning, Build & Validation, Non-Prod Migration, Production Readiness, Production Cutover, and Hypercare & Stabilization. Each phase is gated on defined success criteria. Once the environment is stable on OCI, it transitions to steady-state managed operations, with ITIL-aligned governance, formal backup and DR, and 24x7 monitoring.
PROJECT SUCCESS AGREEMENT
Out of Scope:
Application changes or upgrades, including a JDE 9.2 reimplementation or platform replacement
Modernization roadmap items (Linux web/middleware tiers, reverse proxies, identity and certificate management, Zero Trust), which are a separate future track
Workstream | Outcomes / Deliverables
Discovery & Planning (Weeks 1 - 3) | Validated inventory, dependencies, and performance baseline Future-state architecture and network design Migration, cutover, and testing plan with success criteria
OCI Build, Network & Security (Weeks 4 - 6) | Toptal-managed OCI environment, sized to your workload Private, redundant connectivity to your corporate network Security enclaves protecting legacy systems Backup, DR, and monitoring proven before any data moves
Migration, Testing & Cutover (Weeks 7 - 13) | Dev/test environments migrated first Rehearsed data synchronization and cutover Performance validated against current production
Backup, DR & Stabilization (Weeks 15 - 18) | Weekend cutover with go/no-go checkpoints and full rollback Zero planned data loss Hypercare support through steady-state handoff
Managed Services (36 months) | 24x7 monitoring with SLA-backed availability Ongoing security operations and compliance reporting Managed backup and scheduled DR testing

## Slide 15
APPROACH
Six-Phase Migration Plan (~18 Weeks)
Proposed plan based on our current understanding of scope and effort. Timing is flexible to Rimage's needs and confirmed during discovery.
1
Discovery
& Planning
Weeks 1–3
Baseline, dependency mapping, target design, runbooks
2
Build &
Validation
Weeks 4–6
OCI build, network, security, monitoring, DR readiness
3
Non-Prod
Migration
Weeks 7–9
Migrate dev/test, SQL test, UAT, cutover rehearsal
4
Production
Readiness
Weeks 10–13
Rehearsals, parallel validation, go-live approval
5
Production
Cutover
Week 14
Final sync, weekend cutover, go-live acceptance
6
Hypercare &
Stabilization
Weeks 15–18
Enhanced support, optimization, steady-state handoff
Milestones:
◆ Non-Prod Validation Complete ◆ Production Environment Operational ◆ Transition to Steady-State

## Slide 16: Next Steps
PATH FORWARD
What needs to happen in the next few days.
Owner | Action | Due
[Client] | Provide access to [system / data / environment] | [Date]
[Toptal] | Finalize the Project Success Agreement with the sponsor | [Date]
[Client] | Confirm named reviewer(s) for approvals | [Date]
Notes: Walk each answer aloud and ask the client to confirm or correct. Capture changes live. This is where alignment actually happens — do not rush it. Anything that shifts scope, timeline, or the exclusions gets logged; the PM codifies the final wording with the sponsor after kickoff and secures approval before Discovery.