# Syngenta ARC: the four phases and what happens in each

Internal Toptal working document. Written 2026-09-25 for Kelsey, against the fixed-price four-phase model Syngenta accepted on the 2026-09-24 client call.

This document describes the work in each phase and how each phase is accepted. It carries no hours, no effort and no cost. Sizing lives in effort-pricing-by-role.xlsx, and the reasoning behind it in qa-scope-and-compression-2026-09-22.md. Story keys, acceptance targets and measurement methods are read from the client's own estimation sheet, so nothing here is a Toptal restatement of Syngenta's scope.

# 1. How the four phases fit together

The phases are Syngenta's own, taken from their estimation sheet, with P2 split in two on the dependency seam in that same sheet: every epic in P2b waits on an epic in P2a, so the split falls on a real technical boundary rather than a commercial one. The names still read against the client's plan.

P1 Foundation → P2a Services and Data → P2b Application Surface → P3 Launch.

They run sequentially, as acceptance gates. Each phase has its own deliverables, its own acceptance criteria and its own sign-off, which comes from Mike Magwire and Satya. UAT runs after each phase.

Who builds what. In Buvaneshkumar Balu's own words on the 09-24 call: Syngenta owns the platform layer (Terraform, infrastructure); Toptal owns Arc development. Syngenta also holds the data tier, which is where the ingestion pipelines and the Snowflake model sit. Toptal holds the application: the shell, the ARC micro-frontend, the FastAPI services, and the nomenclature service.

Arc is one application inside a larger Syngenta platform. The platform shell hosts CloudFront and Active Directory. Arc reads Snowflake tables populated by upstream systems (MTA, 1GWAS, GATS-B, GWAS Atlas), all within Syngenta's control. External API integrations are Cogen and Tagasys, and Cogen is the only real external dependency, assessed by Buvanesh at around 95% stable.

# 2. QA: Toptal writes and runs the test automation for all of it

Toptal delivers the QA test automation for every piece of work in the programme, Syngenta-built and Toptal-built alike. This is the position Syngenta stated on the 09-24 call and it is the basis the phases below are written on.

Three things follow from it, and all three belong in the SOW:

- Testing ARC means testing against the full platform. SSO and the integrations are inside the test scope, not adjacent to it. A component-by-component reading was considered and is not what is being delivered.

- The deliverable is automated test scripts, not manual QA. That is the client's own framing, and it is what makes the coverage durable rather than a one-off pass.

- Toptal tests it; whoever built it fixes it. Toptal's deliverable is the script, its execution and the defect report. When a test fails against a Syngenta-built pipeline, dataset or environment, remediation sits with Syngenta. This is the one distinction that has to survive drafting: writing the test for a component is not the same as guaranteeing that component hits its number.

That is why the acceptance tables below name a builder against every row. The test is always Toptal's. The Built by column says who owns the thing being measured, and therefore who acts when it does not pass.

⚠️ Several acceptance targets are numeric and belong to Syngenta-built work (PubMed extraction precision, GWAS Atlas import coverage, trait taxonomy coverage, referential integrity in the Snowflake model, CI/CD quality gates, decommission parity). They are marked Syngenta below. Toptal certifies them; Toptal does not control them.

# 3. The phases

## P1 Foundation

Everything the rest of the programme mounts onto. Syngenta stands up the cloud estate as version-controlled Terraform with CI/CD, monitoring and security controls, and designs and deploys the Snowflake data model in Cogen format. Toptal builds the micro-frontend shell: global navigation, routing, the shared design system, remote mounting for future genomics applications, and the Azure AD / MSAL authentication flow propagated into the remotes.

Nothing in ARC itself is built in this phase. The value of P1 is that the contracts are fixed: the shell onboarding contract, the data model, the environment strategy and the security model are all agreed and in place, so the work that follows is implementation rather than negotiation.

What has to be in place first. Nothing precedes this phase. It does need the decisions that are still open below, in particular the start date and who covers the design work.

The work

| Story | Work | Description | Delivered by |
| --- | --- | --- | --- |
|  | Infrastructure & DevOps (Terraform/IaC) |  |  |
| HS-4766 | Environment & IaC strategy | Define dev/staging/prod strategy and Terraform module structure. | Syngenta |
| HS-4767 | Terraform infra modules | Provision all platform/ARC cloud infra as version-controlled Terraform. | Syngenta |
| HS-4768 | CI/CD pipelines (shell + frontend + backend) | Build/test/deploy pipelines on merge to main; promotion flow; secrets (Key Vault). | Syngenta |
| HS-4769 | Monitoring & alerting | Configure monitoring and alerting for all deployed services. | Syngenta |
| HS-4770 | Pipeline test gates & smoke | Automated quality gates and deployment smoke checks. | Toptal |
| HS-4936 | Security design & threat model | Threat model, auth/RBAC model, data-privacy and trust boundaries for ARC. | Syngenta |
| HS-4937 | Security hardening & RBAC/secrets implementation | RBAC, secrets (Key Vault), platform hardening, dependency/container scanning in CI. | Syngenta |
| HS-4938 | Security & auth negative testing | Negative/abuse-case auth testing and security scanning. | Toptal |
|  | Platform Shell Architecture & Setup |  |  |
| HS-4761 | Shell architecture & app onboarding contract | Define micro-frontend composition (Module Federation/equivalent), release model, and onboarding contract for future genomics apps. | Syngenta |
| HS-4762 | Shell implementation, nav, routing, design system | Build shell, global navigation, app routing, shared design system, remote mounting. | Toptal |
| HS-4763 | Azure AD / MSAL auth integration | Integrate Azure AD/MSAL auth flow into the shell and propagate to remotes. | Toptal |
| HS-4764 | Telemetry & observability wiring | Instrument shell telemetry and route to monitoring stack. | Syngenta |
| HS-4765 | Shell & auth flow test harness | Test composition, navigation, and auth flows end-to-end. | Toptal |
|  | Snowflake Data Model Design |  |  |
| HS-4780 | Cogen schema & entity design | Design MTA/TraitMeasure/Marker/Trial/Haplotype/Study/MtaSet model in Cogen format. | Syngenta |
| HS-4781 | Schema DDL, external results & ontology mapping | Implement schema, external results schema, trait ontology mapping tables. | Syngenta |
| HS-4782 | Data model validation | Validate referential integrity and query patterns. | Toptal |
| HS-4939 | Data governance & classification design | Classification, retention, encryption, ownership and compliance for Snowflake + external sources. | Syngenta |
| HS-4940 | Data governance controls implementation | Encryption, retention, RBAC tagging, classification on Snowflake. | Syngenta |
| HS-4941 | Data governance validation & audit | Validate governance controls and audit classification coverage. | Toptal |

Delivered by is who does the work. Every QA and test-automation row is Toptal's, including the ones testing Syngenta-built components.

Acceptance criteria

In the table below, Built by is who owns the thing being measured, and therefore who remediates a failure. The test itself is always Toptal's.

| # | Story | Criterion | How it is measured | Built by |
| --- | --- | --- | --- | --- |
| P1.1 | HS-4766 | dev/staging/prod strategy & Terraform module structure approved | Architecture review / stakeholder sign-off / approval record | Syngenta |
| P1.2 | HS-4767 | 100% platform infra via Terraform; apply idempotent; zero manual drift | Automated tests / reconciliation reports / validation queries | Syngenta |
| P1.3 | HS-4768 | Build+deploy P90<15min; promotion gated; secrets via Key Vault | Load test / APM / API telemetry | Syngenta |
| P1.4 | HS-4769 | 100% services monitored; alert routing live; MTTA target set | CI reports / reconciliation reports / validation checklist | Syngenta |
| P1.5 | HS-4770 | Quality gates block on fail; deploy smoke 100% pass before promote | Automated tests / reconciliation reports / validation queries | Syngenta |
| P1.6 | HS-4936 | Threat model & security design approved; controls mapped | Architecture review / stakeholder sign-off / approval record | Syngenta |
| P1.7 | HS-4937 | RBAC enforced; secrets in Key Vault; hardening applied; 0 criticals from scan | Automated tests / reconciliation reports / validation queries | Syngenta |
| P1.8 | HS-4938 | Auth negative tests pass; security scan clean; findings remediated | Automated tests / reconciliation reports / validation queries | Toptal |
| P1.9 | HS-4761 | Onboarding contract & MFE composition design approved; reference remote mounts via contract | Architecture review / stakeholder sign-off / approval record | Syngenta |
| P1.10 | HS-4762 | Shell load P50<1.5s, P90<2.5s, P95<3s; remote mount P95<1s | Browser performance telemetry / synthetic test / E2E performance test | Toptal |
| P1.11 | HS-4763 | Auth success 100%; token acquisition P95<800ms; silent refresh works | Automated tests / reconciliation reports / validation queries | Toptal |
| P1.12 | HS-4764 | 100% of shell routes/errors emit telemetry; dashboards live | CI reports / reconciliation reports / validation checklist | Syngenta |
| P1.13 | HS-4765 | E2E coverage of composition/nav/auth; 100% critical-path pass | CI reports / reconciliation reports / validation checklist | Toptal |
| P1.14 | HS-4780 | Cogen-format data model approved by data architect | Architecture review / stakeholder sign-off / approval record | Syngenta |
| P1.15 | HS-4781 | Schema deployed; referential integrity enforced; ontology map loaded | Automated tests / reconciliation reports / validation queries | Syngenta |
| P1.16 | HS-4782 | Referential integrity 100%; representative query patterns validated | Automated tests / reconciliation reports / validation queries | Syngenta |
| P1.17 | HS-4939 | Classification/retention/ownership/compliance documented & approved | Architecture review / stakeholder sign-off / approval record | Syngenta |
| P1.18 | HS-4940 | Controls applied; 100% sensitive fields classified/tagged | Automated tests / reconciliation reports / validation queries | Syngenta |
| P1.19 | HS-4941 | Controls audited; classification coverage validated; gaps logged | CI reports / reconciliation reports / validation checklist | Syngenta |

Certified by Toptal, built and remediated by Syngenta, in this phase: HS-4770 (pipeline test gates & smoke), HS-4782 (data model validation), HS-4941 (data governance validation & audit).

Exit gate. The shell composes and mounts remotes against the published onboarding contract, the authentication flow works end to end including silent token refresh, the Terraform estate applies idempotently with no manual drift, and the Snowflake schema is deployed with referential integrity enforced and the ontology mapping loaded.

## P2a Services and Data

The phase that puts data into ARC and makes it queryable. Syngenta builds the ingestion estate: the MTA Store migration with reconciliation and rollback, the GWAS Atlas ETL, the PubMed and wider literature import with deduplication, the PHG/GATSBY haplotype ingestion, and the canonical trait taxonomy with its Crop Ontology mapping and synonym tables.

Toptal builds the service layer over it: the FastAPI faceted search and detail endpoints against the Snowflake ARC tables, the asynchronous processing tier for long-running queries, the OneGWAS direct-write integration so completed runs land in ARC automatically, and the performance engineering needed to hold sub-second search.

This is the phase with the deepest cross-party dependency. Toptal cannot start the backend until the Snowflake schema exists, and the pipelines Syngenta builds here are the ones carrying the lowest confidence in the whole estimate.

What has to be in place first. The Snowflake schema must be deployed before any Toptal backend work can begin. This is the single hardest dependency in the programme.

| Work in this phase | Waits on | From | Built by |
| --- | --- | --- | --- |
| HS-4777 Faceted search & detail endpoints | HS-4781 Schema DDL, external results & ontology mapping | P1 | Syngenta |
| HS-4942 Performance engineering spike & p95 observability | HS-4781 Schema DDL, external results & ontology mapping | P1 | Syngenta |
| HS-4803 Direct-write integration & error handling | HS-4781 Schema DDL, external results & ontology mapping | P1 | Syngenta |

The work

| Story | Work | Description | Delivered by |
| --- | --- | --- | --- |
|  | ARC Backend (Python/FastAPI) |  |  |
| HS-4776 | API design & OpenAPI contract | Define REST surface over Snowflake; publish/validate OpenAPI spec. | Syngenta |
| HS-4777 | Faceted search & detail endpoints | Implement search/filter/detail endpoints over Snowflake ARC tables. | Toptal |
| HS-4778 | Async/long-running query processing | Task queue (Celery/RQ) for long queries; health checks. | Toptal |
| HS-4779 | Backend integration & load tests | Integration vs Snowflake dev; load test SLAs (sub-second search). | Toptal |
| HS-4942 | Performance engineering spike & p95 observability | Benchmarking, query observability, p95 latency definitions, and a tuning backlog. | Toptal |
|  | GWAS Atlas Integration |  |  |
| HS-4795 | ETL design & relevance criteria | Define ingestion approach and relevance criteria with PO. | Syngenta |
| HS-4796 | GWAS Atlas ETL pipeline | Connect API, transform to unified schema, rate-limit/backoff, incremental refresh, Airflow scheduling. | Syngenta |
| HS-4797 | ETL validation | Validate >90% import coverage and schema-change handling. | Toptal |
|  | MTA Store Data Migration |  |  |
| HS-4783 | Migration & rollback design | Migration approach, parallel-run strategy, rollback plan. | Syngenta |
| HS-4784 | Migration scripts & reconciliation | Repeatable migration scripts; reconciliation reports (counts, keys, integrity). | Syngenta |
| HS-4785 | Migration validation & data quality | Domain-user comparison, data quality issue log, sign-off support. | Toptal |
|  | OneGWAS Direct Write Pipeline |  |  |
| HS-4802 | Output contract & pipeline design | Agree OneGWAS->ARC output format; design automated write. | Syngenta |
| HS-4803 | Direct-write integration & error handling | Write OneGWAS results to Snowflake ARC on completion (variant + PHG/GATSBY); retryable error handling. | Toptal |
| HS-4804 | End-to-end & failure tests | OneGWAS completion -> ARC search <5min; failure/retry validation. | Toptal |
|  | PHG/GATSBY Data Ingestion |  |  |
| HS-4805 | Ingestion & linkage design | Design pull from PHG/GATSBY Snowflake and linkage to ARC schema. | Syngenta |
| HS-4806 | Haplotype ingestion pipeline | Pull pangenome haplotype data and link to association results schema. | Syngenta |
| HS-4807 | Ingestion validation | Validate linkage and completeness. | Toptal |
|  | PubMed / Literature Import |  |  |
| HS-4798 | Multi-source ingestion design | Design unified schema for PubMed/Europe PMC/OpenAlex/ClinVar/dbSNP. | Syngenta |
| HS-4799 | Literature ETL & dedup pipeline | PubMed E-utilities ingestion, dedup, CLI + Airflow scheduling, enrichment linking. | Syngenta |
| HS-4801 | Extraction accuracy & e2e validation | Validate >=85% precision on key fields; end-to-end run. | Toptal |
|  | Trait Taxonomy Definition |  |  |
| HS-4789 | Taxonomy facilitation & governance | Working sessions (Vero/Casey); governance for adding/modifying traits. | Syngenta |
| HS-4790 | Canonical list, ontology map & synonyms | Canonical trait list, Crop Ontology mapping, synonym/alias tables. | Syngenta |
| HS-4791 | Taxonomy review validation | Validate coverage >=80% and approvals. | Toptal |

Delivered by is who does the work. Every QA and test-automation row is Toptal's, including the ones testing Syngenta-built components.

Acceptance criteria

In the table below, Built by is who owns the thing being measured, and therefore who remediates a failure. The test itself is always Toptal's.

| # | Story | Criterion | How it is measured | Built by |
| --- | --- | --- | --- | --- |
| P2a.1 | HS-4776 | OpenAPI spec published & validated (lint clean); reviewed | Architecture review / stakeholder sign-off / approval record | Syngenta |
| P2a.2 | HS-4777 | Search P50<300ms, P90<700ms, P95<1s; detail P95<500ms | Load test / APM / API telemetry | Toptal |
| P2a.3 | HS-4778 | Long queries offloaded; status poll P95<200ms; queue drains; health green | Queue metrics / worker telemetry / health checks | Toptal |
| P2a.4 | HS-4779 | Load test holds SLA: search P95<1s at target concurrency | Load test / APM / API telemetry | Toptal |
| P2a.5 | HS-4942 | p95 targets defined & met (search <1s); query observability live; tuning backlog triaged | Load test / APM / API telemetry | Toptal |
| P2a.6 | HS-4795 | Ingestion approach & relevance criteria agreed with PO | Architecture review / stakeholder sign-off / approval record | Syngenta |
| P2a.7 | HS-4796 | >=90% relevant records imported; incremental refresh scheduled; backoff handles rate limits | CI reports / reconciliation reports / validation checklist | Syngenta |
| P2a.8 | HS-4797 | >=90% import coverage validated; schema-change handling verified | CI reports / reconciliation reports / validation checklist | Syngenta |
| P2a.9 | HS-4783 | Migration / parallel-run / rollback plan approved | Architecture review / stakeholder sign-off / approval record | Syngenta |
| P2a.10 | HS-4784 | Reconciliation: 100% row/key match; integrity pass; zero unexplained deltas | Automated tests / reconciliation reports / validation queries | Syngenta |
| P2a.11 | HS-4785 | Domain-user comparison sign-off; data-quality issue log triaged/closed | Labeled validation set / sampling review / precision report | Syngenta |
| P2a.12 | HS-4802 | OneGWAS->ARC output format & write design agreed | Architecture review / stakeholder sign-off / approval record | Syngenta |
| P2a.13 | HS-4803 | 100% completed runs written; retryable errors recovered; write P95<60s | Automated tests / reconciliation reports / validation queries | Toptal |
| P2a.14 | HS-4804 | OneGWAS completion->ARC searchable P95<5min; failure/retry validated | Pipeline logs / Snowflake write telemetry / E2E test | Toptal |
| P2a.15 | HS-4805 | Pull & linkage-to-ARC design approved | Architecture review / stakeholder sign-off / approval record | Syngenta |
| P2a.16 | HS-4806 | 100% target haplotype records ingested & linked to association schema | CI reports / reconciliation reports / validation checklist | Syngenta |
| P2a.17 | HS-4807 | Linkage & completeness validated (100% sampled keys match) | CI reports / reconciliation reports / validation checklist | Syngenta |
| P2a.18 | HS-4798 | Unified multi-source schema approved | Architecture review / stakeholder sign-off / approval record | Syngenta |
| P2a.19 | HS-4799 | Dedup precision >=95%; incremental ingestion scheduled; enrichment links created | Labeled validation set / sampling review / precision report | Syngenta |
| P2a.20 | HS-4801 | >=85% precision on key fields validated; e2e run green | Labeled validation set / sampling review / precision report | Syngenta |
| P2a.21 | HS-4789 | Trait add/modify governance approved; working sessions held | Architecture review / stakeholder sign-off / approval record | Syngenta |
| P2a.22 | HS-4790 | Canonical list complete; Crop Ontology mapping >=80% coverage; synonyms loaded | CI reports / reconciliation reports / validation checklist | Syngenta |
| P2a.23 | HS-4791 | Coverage >=80% validated; approvals captured | CI reports / reconciliation reports / validation checklist | Syngenta |

Certified by Toptal, built and remediated by Syngenta, in this phase: HS-4797 (etl validation), HS-4785 (migration validation & data quality), HS-4807 (ingestion validation), HS-4801 (extraction accuracy & e2e validation), HS-4791 (taxonomy review validation).

Exit gate. Search and detail endpoints return correct results within their latency targets against migrated and ingested data, all four ingestion pipelines run on their schedules with failure handling proven, the MTA migration reconciles with no unexplained deltas, and the trait taxonomy is approved.

## P2b Application Surface

The scientist-facing product, and almost entirely Toptal-built. The ARC micro-frontend application: faceted search across crop, trait, marker, significance, source and haplotype type, with a paginated sortable results table; the result detail view covering markers, trials, haplotypes and study; and interval-based visualization of PHG/GATSBY haplotype data with variant versus pangenome comparison.

Alongside it, the nomenclature service that resolves trait names and synonyms and handles unmapped terms, and the backend extensions that expose haplotype association results to the application. Syngenta extends the Snowflake schema and views to carry the pangenome haplotype attributes.

This is where the platform becomes something a scientist can use, and where the user-facing performance and accessibility commitments are met.

What has to be in place first. The search and detail endpoints must exist and the data must be in ARC, because the application surface is built directly on them.

| Work in this phase | Waits on | From | Built by |
| --- | --- | --- | --- |
| HS-4772 Faceted search & results table | HS-4777 Faceted search & detail endpoints | P2a | Toptal |
| HS-4773 Result detail & haplotype visualization | HS-4777 Faceted search & detail endpoints | P2a | Toptal |
| HS-4793 Nomenclature service implementation | HS-4790 Canonical list, ontology map & synonyms | P2a | Syngenta |
| HS-4793 Nomenclature service implementation | HS-4777 Faceted search & detail endpoints | P2a | Toptal |
| HS-4810 Haplotype search/filter endpoints | HS-4806 Haplotype ingestion pipeline | P2a | Syngenta |
| HS-4810 Haplotype search/filter endpoints | HS-4777 Faceted search & detail endpoints | P2a | Toptal |

The work

| Story | Work | Description | Delivered by |
| --- | --- | --- | --- |
|  | ARC Micro-Frontend Application (Next.js) |  |  |
| HS-4771 | Frontend component architecture | Define ARC remote structure, state, and integration with shell. | Syngenta |
| HS-4772 | Faceted search & results table | Filtering by crop/trait/marker/significance/source/haplotype type; paginated sortable results. | Toptal |
| HS-4773 | Result detail & haplotype visualization | Detail view (markers/trials/haplotypes/study) and PHG/GATSBY interval-based visualization. | Toptal |
| HS-4775 | Frontend unit, integration, a11y & perf tests | Coverage >=80%, key-flow integration, sub-second search, accessibility. | Toptal |
|  | Back-end changes to support PHG/GATSBY haplotypes |  |  |
| HS-4812 | Backend haplotype support design | Define API/data-access changes for pangenome haplotype results. | Syngenta |
| HS-4813 | Haplotype API & data access | Implement backend endpoints/data access for haplotype association results. | Toptal |
| HS-4814 | Schema extensions for haplotypes | Extend ARC schema/views to support pangenome haplotype attributes. | Syngenta |
| HS-4815 | Backend haplotype tests | Integration tests for haplotype endpoints. | Toptal |
|  | Nomenclature Service |  |  |
| HS-4792 | Service interface design | Define API/module contract for trait resolution and synonym lookup. | Syngenta |
| HS-4793 | Nomenclature service implementation | Resolution, synonym lookup, unmapped handling; ARC backend integration. | Toptal |
| HS-4794 | Service tests & performance | Correct resolution for all mapped traits; <200ms lookups. | Toptal |
|  | PHG/GATSBY Search, Filtering & Visualization |  |  |
| HS-4808 | Haplotype search/viz design | Define haplotype-type filtering and interval visualization approach. | Syngenta |
| HS-4809 | Haplotype filter, indicator & interval viz | Faceted haplotype-type filter, result indicator, interval-based detail, variant vs pangenome compare. | Toptal |
| HS-4810 | Haplotype search/filter endpoints | Endpoints supporting haplotype-type filtering and comparison data. | Toptal |
| HS-4811 | Search & visualization tests | Validate filters, comparison, and rendering. | Toptal |

Delivered by is who does the work. Every QA and test-automation row is Toptal's, including the ones testing Syngenta-built components.

Acceptance criteria

In the table below, Built by is who owns the thing being measured, and therefore who remediates a failure. The test itself is always Toptal's.

| # | Story | Criterion | How it is measured | Built by |
| --- | --- | --- | --- | --- |
| P2b.1 | HS-4771 | ARC remote structure/state/shell-integration design approved | Architecture review / stakeholder sign-off / approval record | Syngenta |
| P2b.2 | HS-4772 | Results render P50<400ms, P90<800ms, P95<1s (excl. network) | Browser performance telemetry / synthetic test / E2E performance test | Toptal |
| P2b.3 | HS-4773 | Detail view P90<1s; interval viz render P95<1.5s | Browser performance telemetry / synthetic test / E2E performance test | Toptal |
| P2b.4 | HS-4775 | Unit coverage >=80%; key-flow integration green; search <1s; a11y pass | CI reports / reconciliation reports / validation checklist | Toptal |
| P2b.5 | HS-4812 | API/data-access changes for haplotype results approved | Architecture review / stakeholder sign-off / approval record | Syngenta |
| P2b.6 | HS-4813 | Haplotype endpoints P95<1s; correct results vs fixtures | Load test / APM / API telemetry | Toptal |
| P2b.7 | HS-4814 | Schema/views extended; integrity preserved; haplotype attrs queryable | Automated tests / reconciliation reports / validation queries | Syngenta |
| P2b.8 | HS-4815 | Haplotype endpoint integration tests green (100% critical paths) | Automated tests / reconciliation reports / validation queries | Toptal |
| P2b.9 | HS-4792 | Resolution & synonym-lookup API/module contract approved | Architecture review / stakeholder sign-off / approval record | Syngenta |
| P2b.10 | HS-4793 | Resolution correct for all mapped traits; lookup P95<200ms | Load test / APM / API telemetry | Toptal |
| P2b.11 | HS-4794 | 100% mapped-trait resolution correct; lookup P95<200ms | Load test / APM / API telemetry | Toptal |
| P2b.12 | HS-4808 | Haplotype filtering & interval-viz approach approved | Architecture review / stakeholder sign-off / approval record | Syngenta |
| P2b.13 | HS-4809 | Filtered results P90<1s; interval viz P95<1.5s; variant vs pangenome compare works | Load test / APM / API telemetry | Toptal |
| P2b.14 | HS-4810 | Haplotype filter endpoint P95<1s | Load test / APM / API telemetry | Toptal |
| P2b.15 | HS-4811 | Filters, comparison & rendering validated across haplotype types | Automated tests / reconciliation reports / validation queries | Toptal |

Exit gate. The full journey from faceted search to result detail and haplotype visualization works against live data within the stated render targets, unit coverage is at or above 80%, the accessibility pass is green, and trait resolution is correct for every mapped trait.

## P3 Launch

Proving the whole platform works together, handing it over, and retiring what it replaces. Integration testing runs every data flow and every UI and API critical path in staging at production-like volume, covering performance against the stated SLAs, authentication and security, and cross-browser behaviour on Chrome and Edge.

UAT then runs with the scientist groups, with defects triaged and tracked to closure, followed by a hardening iteration that closes every critical and high before cutover. Training materials and user documentation are produced. Syngenta deploys to production, confirms monitoring and alerting, and runs the hypercare window with triage and fix SLAs and on-call handover.

The MTA Store is decommissioned last: feature parity confirmed, dependents redirected to ARC and Snowflake, and legacy traffic observed at zero before anything is shut down.

What has to be in place first. The application surface must be complete, since integration testing and UAT run against the whole assembled platform rather than against components.

| Work in this phase | Waits on | From | Built by |
| --- | --- | --- | --- |
| HS-4826 Test data & fixtures support | HS-4781 Schema DDL, external results & ontology mapping | P1 | Syngenta |

The work

| Story | Work | Description | Delivered by |
| --- | --- | --- | --- |
|  | Integration Testing |  |  |
| HS-4824 | Integration test plan | Plan covering all data flows and UI/API critical paths. | Syngenta |
| HS-4825 | Integration, perf, security & cross-browser suites | All flows in staging at prod-like volume; SLA perf; auth/security; Chrome/Edge. | Toptal |
| HS-4826 | Test data & fixtures support | Provide test data, fixtures, and environment support. | Toptal |
| HS-4943 | Pre-launch hardening & stabilization iteration | Bug-fix/remediation iteration after integration & UAT; close criticals/highs before cutover. | Toptal |
|  | MTA Store Decommission |  |  |
| HS-4786 | Decommission plan | Feature-parity confirmation plan and read-only transition window. | Syngenta |
| HS-4787 | Infra teardown & redirects | Shut down legacy infra/ETL; redirect dependents to ARC/Snowflake. | Syngenta |
| HS-4788 | Parity & usage-zero confirmation | Confirm parity and zero traffic before decommission. | Toptal |
|  | Production Deployment & Go-Live |  |  |
| HS-4830 | Go-live plan & ops handover | Production cutover plan; operational runbook handover. | Syngenta |
| HS-4831 | Production deployment & monitoring | Deploy platform+ARC to prod; smoke tests; confirm monitoring/alerting. | Syngenta |
| HS-4832 | Production smoke & post-deploy validation | Prod smoke tests; 48h defect watch. | Toptal |
| HS-4944 | Hypercare & post-go-live support | Post-launch hypercare window: triage/fix SLAs, monitoring, on-call handover, reserved bug-fix capacity (beyond 48h watch). | Syngenta |
|  | UAT & User Training |  |  |
| HS-4827 | UAT coordination & sign-off | Coordinate scientist UAT groups and acceptance sign-off. | Syngenta |
| HS-4828 | UAT execution & defect triage | Run UAT cycles; triage and track defects. | Toptal |
| HS-4829 | Training materials & documentation | Produce training materials and user documentation. | Toptal |

Delivered by is who does the work. Every QA and test-automation row is Toptal's, including the ones testing Syngenta-built components.

Acceptance criteria

In the table below, Built by is who owns the thing being measured, and therefore who remediates a failure. The test itself is always Toptal's.

| # | Story | Criterion | How it is measured | Built by |
| --- | --- | --- | --- | --- |
| P3.1 | HS-4824 | Integration test plan covering all data flows & UI/API critical paths approved | Architecture review / stakeholder sign-off / approval record | Syngenta |
| P3.2 | HS-4825 | All flows green at prod-like volume; SLA (search P95<1s); auth/security pass; Chrome/Edge | Load test / APM / API telemetry | Toptal |
| P3.3 | HS-4826 | Test data/fixtures cover all integration scenarios; envs supported | CI reports / reconciliation reports / validation checklist | Toptal |
| P3.4 | HS-4943 | Hardening iteration closes all criticals/highs; full regression green pre-cutover | Automated tests / reconciliation reports / validation queries | Toptal |
| P3.5 | HS-4786 | Feature-parity & read-only transition plan approved | Architecture review / stakeholder sign-off / approval record | Syngenta |
| P3.6 | HS-4787 | Legacy infra/ETL down; 100% dependents redirected to ARC/Snowflake | Automated tests / reconciliation reports / validation queries | Syngenta |
| P3.7 | HS-4788 | Parity confirmed; legacy traffic = 0 over watch window before decommission | Automated tests / reconciliation reports / validation queries | Syngenta |
| P3.8 | HS-4830 | Cutover plan & ops runbook handover approved | Architecture review / stakeholder sign-off / approval record | Syngenta |
| P3.9 | HS-4831 | Platform+ARC deployed to prod; smoke 100% pass; monitoring confirmed; uptime >=99.5% | Monitoring dashboard / uptime report / incident log | Syngenta |
| P3.10 | HS-4832 | Prod smoke 100% pass; 48h defect watch clean | Automated tests / reconciliation reports / validation queries | Toptal |
| P3.11 | HS-4944 | Hypercare window staffed; triage/fix SLAs met; monitoring & on-call handover complete; bug-fix capacity reserved | Monitoring dashboard / uptime report / incident log | Syngenta |
| P3.12 | HS-4827 | UAT groups coordinated; acceptance sign-off obtained | Architecture review / stakeholder sign-off / approval record | Syngenta |
| P3.13 | HS-4828 | UAT cycles run; defects triaged/tracked; no open criticals at exit | Automated tests / reconciliation reports / validation queries | Toptal |
| P3.14 | HS-4829 | Training materials & user docs delivered & reviewed | Architecture review / stakeholder sign-off / approval record | Toptal |

Certified by Toptal, built and remediated by Syngenta, in this phase: HS-4788 (parity & usage-zero confirmation).

Exit gate. Integration suites are green at production-like volume, UAT has exited with no open criticals, the hardening iteration has closed all criticals and highs, production smoke passes with the defect watch clean, and the MTA Store is confirmed at zero traffic before decommission.

# 4. What is still open

Scope questions only. Commercial and sizing items are tracked in project-context.md and the pricing workbook.

| # | Open item |
| --- | --- |
| 1 | Who covers the design work (D9). No design or UX role appears anywhere in the sheet, on either side, for a scientist-facing interface with a design system, faceted search and interval visualization |
| 2 | The start date (D20). No date has been agreed with Syngenta, and the phase sequence hangs off it |
| 3 | UAT scope boundaries and change-order triggers. Agreed on the call, not yet written. Upstream Snowflake schema changes and API taxonomy shifts are the triggers |
| 4 | Coding standards and delivery documentation, needed before onboarding: merge request process, code review gates, unit and integration test requirements |
| 5 | Who tests Syngenta's half if a failure is theirs. Toptal certifies it; the remediation path has not been written down |
| 6 | What requires the asynchronous task queue (HS-4778), on a platform targeting sub-second search |

Two things that are settled and worth not reopening: UAT sits inside the fixed price with its boundaries defined in the contract, and changes outside Toptal's control that force extra cycles are handled by change order. And "maintenance" means in-flight test script upkeep during development, not a post-launch phase.